## Slide 1: Budget Preparation Calendar
Month | Activity | Stakeholders | Output
January | Carry out the macroeconomic projections | MPI, MoF, Lao Academia for Socio-Economic Research, BoL, MoIC | Macroeconomic projections
February | Macroeconomic projections shared with MoF | MoF | 
March | Forecast/estimation of the overall medium-term resource envelope for the State Budget Plan Notify MPI the public investment envelop | MoF MPI | Medium-term state budget revenue Medium-term state budget expenditure State budget balance
April | Notify the Tier 1 Budget Units the medium-term revenue figures and the medium-term recurrent budget ceilings Notify the Tier 1 Budget Units the public investment ceilings and provide the public investment planning manual/guidelines | Tier 1 SUs Tier 1 SUs | Tier 1 Recurrent Budget Ceilings and revenue figures Tier 1 Public investment ceilings
May | Tier 1-Central allocate Budget ceilings to Tier 2 units Tier 2-Provinces allocate Budget ceilings to Tier 2 units | NA, MoF, T1 SUs Provincial Assemblies, Finance Dept & local offices | Tier 2 sub-ceilings for Central units Tier 2 sub-ceilings for Provincial units
June | Tier 2 SUs submit their MTB plans to Tier 1 units | Tier 2 SUs | Tier 2 Medium term Budget

## Slide 2: Budget Preparation Calendar
Month | Activity | Stakeholder | Output
July | Tier 1 consolidates the medium-term budget plans of all of its Tier 2 budget units and submit Budget policy statement to MoF | Tier 1 SUs | Budget Policy statement- Summary report of the execution of the annual state budget plan of the previous fiscal year Summary report on the execution of the annual state budget plan for the current fiscal year Medium-term budget revenue and expenditure policies Proposed budget plan for the next years based on the COA and the planned allocations based on their priorities and work plan
August | Consolidation of all public investments plans nation-wide classified by externally and domestically financed projects of Tier 1 SUs at central & local level and submit consolidated public investment plan | MPI | Public Investment Plan Macroeconomic indicators/values
August | Consolidating and drafting the medium-term state budget plan and submit the State Budget Policy Statement (SBPS) by MoF to GoL | MoF | State Budget Policy Statement- Macroeconomic circumstances Fiscal policies and estimation of the medium-term aggregate resource envelop Annual state budget plan Fiscal risks